## Plan
Phase | Task | Owner | Due | Est (hrs) | Status | Notes
Vision & design | Check Lottie's September holidays, lock the date | Liv | 3 Jul | 0.5 | Not started | Gates everything. Confirm before booking anything
| Set the budget ceiling | Liv | 3 Jul | 1 | Not started | Needed before venue hunt
| Confirm objective and success metrics | Liv | 3 Jul | 0.5 | Not started | Reputation-led: posts, calibre of host, shareable output. Pin the numbers
| Define what attendees build | Liv / host | 14 Aug | 2 | Not started | Drives host choice. Must be genuinely shareable and useful Monday morning
| Agree run of day and flow with host | Liv / host | 21 Aug | 3 | Not started | Present-to-50 open, then breakouts. Build in the Up Club touches
Logistics | Secure the AI host | Liv | 24 Jul | 3 | Not started | The long pole. A credible, known practitioner carries the brand. Start now
| Shortlist venues | Nzola | 17 Jul | 2 | Not started | Power for 50 laptops + reliable wifi + present-to-50 + breakouts. Up Club feel, not corporate
| Book venue and walkthrough | Liv / Nzola | 31 Jul | 1 | Not started | Confirm power, wifi, screen, set-up access time
| Book photographer | Nzola | 14 Aug | 0.5 | Not started | Brief: come early for set-up/brand shots, close-up and candid, not empty-room
| Sort catering (lunch + drinks) | Nzola | 21 Aug | 1.5 | Not started | Ask if any attendee is from an f&d brand first, they often sponsor
| Check / order merch | Nzola | 21 Aug | 0.5 | Not started | Totes, notebooks, stickers. Pre-pack totes, they take ages
| Confirm team on the day and roles | Liv / Nzola | 21 Aug | 0.5 | Not started | Brief everyone to work the room individually, not cluster
| Tech check plan (laptops, power, wifi, screen) | Nzola | 28 Aug | 1 | Not started | Test the wifi can take 50 devices. Make-or-break
Comms & marketing | Set up Luma page (copy + graphics) | Liv / Nzola | 31 Jul | 3 | Not started | HARD DEADLINE. Gates all marketing. Brand it Up Club, not Up World
| Member email: save the date | Nzola | 4 Aug | 0.5 | Not started
| Member email: get your spot (+ second push) | Nzola | 18 Aug | 1 | Not started
| Include in Sept onboarding / WCU emails | Nzola | Aug (ongoing) | 0.5 | Not started
| Slack posts to members | Nzola | Aug (ongoing) | 0.5 | Not started
| LinkedIn: Up World + Lottie + Liv | Lottie / Liv | Aug (ongoing) | 1 | Not started | Building-out-loud energy, part of the reputation play
| Selectively invite past-cohort leads | Liv | from 18 Aug | 2 | Not started | Based on who's signed up. Hot leads from previous cohorts
| Reminder workflow (1 week + 1 day before) | Nzola | 28 Aug | 0.5 | Not started | Joining details, what to bring (charged laptop!)
On the day | Final shopping list | Nzola | day before | 0.2 | Not started
| Print guest list + register | Nzola | day before | 0.2 | Not started | For ticking in and making intros
| Print signage | Nzola | day before | 0.2 | Not started | Up Club branded
| Set-up: tables, breakouts, power/charging, totes | All | event AM | 1.5 | Not started | Get in early. Test wifi and power first thing
| Someone warm on the door | Nzola | event |  | Not started | Hugs not handshakes
| Run of day with timings | Liv | event |  | Not started | Lottie opens, host leads build, breakouts, share-back
| Team working the room | All | event |  | Not started | Spread out, make industry intros, help people connect
Post-event | Upload photos to Drive (members can see) | Nzola | +1 day | 0.3 | Not started
| Next-day email: photos + builds + feedback ask | Nzola | +1 day | 0.5 | Not started
| Reshare attendee LinkedIn posts, interact | Liv / Lottie | +1 week | 0.5 | Not started | This IS the reputation outcome. Push it hard
| Chase feedback (DM non-responders) | Nzola | +1 week | 0.3 | Not started
| Convert invited leads to members | Liv | +1 month | 2 | Not started
| Capture learnings in the running doc | Liv / Nzola | +1 week | 0.3 | Not started

## Budget
Line | Forecast (£) | Actual (£) | Notes
Venue |  |  | Needs power + wifi for 50 + breakouts
AI host fee
Photography
Food & drink (lunch + drinks) |  |  | Often partly sponsored by member brands
Merch |  |  | Totes, notebooks, stickers
Printing |  |  | Signage, name cards
Other / buffer
Total | 0 | 0

## Food & drink
Brand | Category | What they give | Contact | Status | Delivery
Reach out 2-4 weeks ahead. Confirm delivery 1-2 weeks before.